## Answer Report 1
Microsoft Excel 14.0 Answer Report
Worksheet: [Earth Mover Example--Crashing.xlsx]Sheet1
Report Created: 8/17/2012 12:07:55 PM
Result: Solver found a solution. All Constraints and optimality conditions are satisfied.
Solver Engine
Engine: Simplex LP
Solution Time: 0 Seconds.
Iterations: 17 Subproblems: 0
Solver Options
Max Time Unlimited, Iterations Unlimited, Precision 0.000001
Max Subproblems Unlimited, Max Integer Sols Unlimited, Integer Tolerance 1%, Assume NonNegative
Objective Cell (Min)
| Cell | Name | Original Value | Final Value
| $T$6 | Cost Crashing cost (in $1,000s) | 0 | 200
Variable Cells
| Cell | Name | Original Value | Final Value | Integer
| $B$4 | Value XA | 6 | 5 | Contin
| $C$4 | Value XB | 10 | 9 | Contin
| $D$4 | Value XC | 9 | 9 | Contin
| $E$4 | Value XD | 16 | 18 | Contin
| $F$4 | Value XE | 20 | 16 | Contin
| $G$4 | Value XF | 20 | 16 | Contin
| $H$4 | Value XG | 16 | 18 | Contin
| $I$4 | Value XH | 22 | 24 | Contin
| $J$4 | Value XI | 24 | 26 | Contin
| $K$4 | Value YA | 0 | 1 | Contin
| $L$4 | Value YB | 0 | 0 | Contin
| $M$4 | Value YC | 0 | 0 | Contin
| $N$4 | Value YD | 0 | 0 | Contin
| $O$4 | Value YE | 0 | 0 | Contin
| $P$4 | Value YF | 0 | 3 | Contin
| $Q$4 | Value YG | 6 | 0 | Contin
| $R$4 | Value YH | 0 | 0 | Contin
| $S$4 | Value YI | 0 | 0 | Contin
Constraints
| Cell | Name | Cell Value | Formula | Status | Slack
| $T$17 | EF for activity A Total | 6 | $T$17>=$V$17 | Binding | 0
| $T$18 | EF for activity B Total | 4 | $T$18>=$V$18 | Binding | 0
| $T$19 | EF for activity C Total | 4 | $T$19>=$V$19 | Not Binding | 1
| $T$20 | EF for activity D Total | 9 | $T$20>=$V$20 | Not Binding | 3
| $T$21 | EF for activity E Total | 7 | $T$21>=$V$21 | Not Binding | 4
| $T$22 | EF for activity F Total | 10 | $T$22>=$V$22 | Binding | 0
| $T$23 | EF for activity F Total | 10 | $T$23>=$V$23 | Binding | 0
| $T$24 | EF for activity G Total | 2 | $T$24>=$V$24 | Binding | 0
| $T$25 | EF for activity G Total | 2 | $T$25>=$V$25 | Binding | 0
| $T$26 | EF for activity H Total | 6 | $T$26>=$V$26 | Binding | 0
| $T$27 | EF for activity I Total | 8 | $T$27>=$V$27 | Binding | 0
| $T$28 | EF for activity I Total | 8 | $T$28>=$V$28 | Binding | 0
| $T$29 | Completion time Total | 24 | $T$29<=$V$29 | Not Binding | 2
| $T$30 | Completion time Total | 26 | $T$30<=$V$30 | Binding | 0
| $T$8 | Limit on activity A crashing Total | 1 | $T$8<=$V$8 | Binding | 0
| $T$9 | Limit on activity B crashing Total | 0 | $T$9<=$V$9 | Binding | 0
| $T$10 | Limit on activity C crashing Total | 0 | $T$10<=$V$10 | Not Binding | 1
| $T$11 | Limit on activity D crashing Total | 0 | $T$11<=$V$11 | Not Binding | 3
| $T$12 | Limit on activity E crashing Total | 0 | $T$12<=$V$12 | Not Binding | 1
| $T$13 | Limit on activity F crashing Total | 3 | $T$13<=$V$13 | Binding | 0
| $T$14 | Limit on activity G crashing Total | 0 | $T$14<=$V$14 | Binding | 0
| $T$15 | Limit on activity H crashing Total | 0 | $T$15<=$V$15 | Not Binding | 1
| $T$16 | Limit on activity I crashing Total | 0 | $T$16<=$V$16 | Not Binding | 4

## Sensitivity Report 1
Microsoft Excel 14.0 Sensitivity Report
Worksheet: [Earth Mover Example--Crashing.xlsx]Sheet1
Report Created: 8/17/2012 12:07:55 PM
Variable Cells
|  |  | Final | Reduced | Objective | Allowable | Allowable
| Cell | Name | Value | Cost | Coefficient | Increase | Decrease
| $B$4 | Value XA | 5 | 0 | 0 | 1e+30 | 55
| $C$4 | Value XB | 9 | 0 | 0 | 1e+30 | 55
| $D$4 | Value XC | 9 | 0 | 0 | 0 | 55
| $E$4 | Value XD | 18 | 0 | 0 | 0 | 15
| $F$4 | Value XE | 16 | 0 | 0 | 0 | 15
| $G$4 | Value XF | 16 | 0 | 0 | 1e+30 | 15
| $H$4 | Value XG | 18 | 0 | 0 | 1e+30 | 15
| $I$4 | Value XH | 24 | 0 | 0 | 350 | 0
| $J$4 | Value XI | 26 | 0 | 0 | 75 | 1e+30
| $K$4 | Value YA | 1 | 0 | 20 | 55 | 1e+30
| $L$4 | Value YB | 0 | 0 | 0 | 75 | 1e+30
| $M$4 | Value YC | 0 | 50 | 50 | 1e+30 | 50
| $N$4 | Value YD | 0 | 50 | 50 | 1e+30 | 50
| $O$4 | Value YE | 0 | 70 | 70 | 1e+30 | 70
| $P$4 | Value YF | 3 | 0 | 60 | 15 | 1e+30
| $Q$4 | Value YG | 0 | 0 | 0 | 75 | 1e+30
| $R$4 | Value YH | 0 | 350 | 350 | 1e+30 | 350
| $S$4 | Value YI | 0 | 0 | 75 | 1e+30 | 15
Constraints
|  |  | Final | Shadow | Constraint | Allowable | Allowable
| Cell | Name | Value | Price | R.H. Side | Increase | Decrease
| $T$17 | EF for activity A Total | 6 | 75 | 6 | 2 | 0
| $T$18 | EF for activity B Total | 4 | 75 | 4 | 2 | 0
| $T$19 | EF for activity C Total | 4 | 0 | 3 | 1 | 1e+30
| $T$20 | EF for activity D Total | 9 | 0 | 6 | 3 | 1e+30
| $T$21 | EF for activity E Total | 7 | 0 | 3 | 4 | 1e+30
| $T$22 | EF for activity F Total | 10 | 75 | 10 | 2 | 0
| $T$23 | EF for activity F Total | 10 | 0 | 10 | 1 | 1e+30
| $T$24 | EF for activity G Total | 2 | 0 | 2 | 4 | 1e+30
| $T$25 | EF for activity G Total | 2 | 75 | 2 | 2 | 0
| $T$26 | EF for activity H Total | 6 | 0 | 6 | 2 | 24
| $T$27 | EF for activity I Total | 8 | 0 | 8 | 3 | 1e+30
| $T$28 | EF for activity I Total | 8 | 75 | 8 | 4 | 0
| $T$29 | Completion time Total | 24 | 0 | 26 | 1e+30 | 2
| $T$30 | Completion time Total | 26 | -75 | 26 | 0 | 4
| $T$8 | Limit on activity A crashing Total | 1 | -55 | 1 | 0 | 1
| $T$9 | Limit on activity B crashing Total | 0 | -75 | 0 | 0 | 0
| $T$10 | Limit on activity C crashing Total | 0 | 0 | 1 | 1e+30 | 1
| $T$11 | Limit on activity D crashing Total | 0 | 0 | 3 | 1e+30 | 3
| $T$12 | Limit on activity E crashing Total | 0 | 0 | 1 | 1e+30 | 1
| $T$13 | Limit on activity F crashing Total | 3 | -15 | 3 | 0 | 2
| $T$14 | Limit on activity G crashing Total | 0 | -75 | 0 | 0 | 0
| $T$15 | Limit on activity H crashing Total | 0 | 0 | 1 | 1e+30 | 1
| $T$16 | Limit on activity I crashing Total | 0 | 0 | 4 | 1e+30 | 4

## Sheet1
Earth Mover Example--Crashing
| Eariliest Finish Times | [8 empty] | Amount of crashing (in weeks)
| XA | XB | XC | XD | XE | XF | XG | XH | XI | YA | YB | YC | YD | YE | YF | YG | YH | YI
Value | 5 | 9 | 9 | 18 | 16 | 16 | 18 | 24 | 26 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
Crashing cost (in $1,000s)
Cost | Amount of crashing (in weeks) YA: 20; Amount of crashing (in weeks) YB: 0; Amount of crashing (in weeks) YC: 50; Amount of crashing (in weeks) YD: 50; Amount of crashing (in weeks) YE: 70; Amount of crashing (in weeks) YF: 60; Amount of crashing (in weeks) YG: 0; Amount of crashing (in weeks) YH: 350; Amount of crashing (in weeks) YI: 75 | 200
[19 empty] | Total |  | RHS
Limit on activity A crashing | [18 empty] | 1 | <= | 1 | bar: Amount of crashing (in weeks) YA
Limit on activity B crashing | [18 empty] | 0 | <= | 0 | bar: Amount of crashing (in weeks) YB
Limit on activity C crashing | [18 empty] | 0 | <= | 1 | bar: Amount of crashing (in weeks) YC
Limit on activity D crashing | [18 empty] | 0 | <= | 3 | bar: Amount of crashing (in weeks) YD
Limit on activity E crashing | [18 empty] | 0 | <= | 1 | bar: Amount of crashing (in weeks) YE
Limit on activity F crashing | [18 empty] | 3 | <= | 3 | bar: Amount of crashing (in weeks) YF
Limit on activity G crashing | [18 empty] | 0 | <= | 0 | bar: Amount of crashing (in weeks) YG
Limit on activity H crashing | [18 empty] | 0 | <= | 1 | bar: Amount of crashing (in weeks) YH
Limit on activity I crashing | [18 empty] | 0 | <= | 4 | bar: Amount of crashing (in weeks) YI
EF for activity A | [18 empty] | 6 | >= | 6 | bar: Eariliest Finish Times XA; Amount of crashing (in weeks) YA
EF for activity B | [18 empty] | 4 | >= | 4 | bar: Eariliest Finish Times XA to Eariliest Finish Times XB; Amount of crashing (in weeks) YB
EF for activity C | [18 empty] | 4 | >= | 3 | bar: Eariliest Finish Times XA; Eariliest Finish Times XC; Amount of crashing (in weeks) YC
EF for activity D | [18 empty] | 9 | >= | 6 | bar: Eariliest Finish Times XB; Eariliest Finish Times XD; Amount of crashing (in weeks) YD
EF for activity E | [18 empty] | 7 | >= | 3 | bar: Eariliest Finish Times XB; Eariliest Finish Times XE; Amount of crashing (in weeks) YE
EF for activity F | [18 empty] | 10 | >= | 10 | bar: Eariliest Finish Times XB; Eariliest Finish Times XF; Amount of crashing (in weeks) YF
EF for activity F | [18 empty] | 10 | >= | 10 | bar: Eariliest Finish Times XC; Eariliest Finish Times XF; Amount of crashing (in weeks) YF
EF for activity G | [18 empty] | 2 | >= | 2 | bar: Eariliest Finish Times XE; Eariliest Finish Times XG; Amount of crashing (in weeks) YG
EF for activity G | [18 empty] | 2 | >= | 2 | bar: Eariliest Finish Times XF to Eariliest Finish Times XG; Amount of crashing (in weeks) YG
EF for activity H | [18 empty] | 6 | >= | 6 | bar: Eariliest Finish Times XG to Eariliest Finish Times XH; Amount of crashing (in weeks) YH
EF for activity I | [18 empty] | 8 | >= | 8 | bar: Eariliest Finish Times XD; Eariliest Finish Times XI; Amount of crashing (in weeks) YI
EF for activity I | [18 empty] | 8 | >= | 8 | bar: Eariliest Finish Times XG; Eariliest Finish Times XI; Amount of crashing (in weeks) YI
Completion time | [18 empty] | 24 | <= | 26 | bar: Eariliest Finish Times XH
Completion time | [18 empty] | 26 | <= | 26 | bar: Eariliest Finish Times XI